## Slide 1: The Web Accessibility in Higher Education Project
Some lessons learned from coordinating a statewide digital accessibility initiative

## Slide 2: WAHEP
Statewide effort
Focus on web and digital accessibility in higher education
Two broad focus areas
  Institution level
  Nuts and bolts

## Slide 3: WAHEP Partners
Oklahoma ABLE Tech, WebAIM, National Center on Disability and Access to Education (NCDAE), Southwest ADA Center, OK Department of Rehabilitation Services.

## Slide 4: Components
26 institutional teams
Two day, on-site training in Fall, 2012
Ongoing webinar series
  Policy development
  Project teams
  Accessible documents
  Common barriers in higher education sites
  Evaluating web sites for accessibility

## Slide 5: Additional Support
Remote workshops, September, 2013
On site visits
Project web site at http://www.ok.gov/abletech/IT_Accessibility/WAHEP/
Weekly Web Accessibility Tips
ABLE Tech
WebAIM
NCDAE

## Slide 6: Ties that Bind
Memoranda of Understanding
  Policy
  Primary web site accessibility
Common across teams
Supported by State Regents
Catalyst for action

## Slide 7: Comparing Three Institutions
Institutions’ experiences vary
Patterns do emerge
Adding to this knowledge base throughout the academic year

## Slide 8: Institution A
Larger institution
Led with accessibility policy
Small policy committee that remained small
  Policy scope broadened
Policy published in less than one year
Presence of strong advocates
Committee has since grown

## Slide 9: Institution A Pro and Con
Pros
Policy group was agile
Policy received support from leadership
Policy adopted quickly
Committee involved student, faculty with disabilities
Cons
Small committee, narrow focus
  Magnifies turnover
  Limits involvement
Implementation lags behind

## Slide 10: Institution B
Larger institution
Policy group began small, but grew organically
Policy and implementation often discussed in tandem
Moving toward policy, implementation plan and resource plan

## Slide 11: Institution B Pro and Con
Pros
Broad policy
Broad initiative
Broad involvement
Recognition that investment is required
  Willingness to ask
Cons
Slower process
Larger committee
No one with a disability is part of the conversation

## Slide 12: Institution C
Small-medium sized institution
Work digital accessibility into some staff training and resources
No formal policy in place
  Draft has floated around for a while

## Slide 13: Institution C Pro and Con
Pros
Taking action quickly
Using existing structures on campus
  Build in, don’t bolt on
Cons
Can get the cart before the horse
Not campus wide in reach
Limited or narrow administrative support

## Slide 14: Recurring Themes
Needs
  Subject matter expertise
  Answer to “why are we doing this?”
  Broad administrative support
  A representative, but appropriately sized, team
  An understanding of how stuff works

## Slide 15: Find or Make a Unicorn
Find someone with
  Motivation
  Knowledge
Give someone
  Time
  Training
  Resources
  Support from leadership
Notes: SME

## Slide 16: Institutional Motivation
Sure, it’s the right thing to do. But why?
  Direct benefits to people with disabilities
    Recruit students, faculty, staff with disabilities
    Ensure better outcomes for education and employment
  Benefit to broad audience
    Content clarity with focus on the message getting through
    Lowering the barriers for everyone
    Multimodal learning and captioning
    Make life easier for content authors
    Help risk management to sleep better
Notes: Why are we doing this?

## Slide 17: Getting the Institution on the Bandwagon
The right advocate
The right message
The right audience
Notes: Administrative support

## Slide 18: Team Building
Team composition
  Administration
  Technical
  Content
  Legal
  Purchasing
  PWD
Stakeholders vs. Task Force
Notes: Right sized team

## Slide 19: Once Assembled…
Team focus areas
  Policy
  Implementation
    Timeline, approach, standards
Use the team
Notes: Right sized team

## Slide 20: How Stuff Works
Apply accessibility to existing processes and functions
  Understand where the good fit is
  Understand how to fit it in
  Tailor information, training and resources for the audience
Create efficiency and redundancy

## Slide 21: Where to Find the Right Fit
Procurement
Design templates and code libraries
Style guides and related training
LMS, CMS training
HR, other technical training
Hiring

## Slide 22: In the WAHEP Testing Lab
Help apply lessons to individual institutions
More remote workshops and support
More on-site presence
Other interactive media
Putting some weight behind the effort

## Slide 23: Thanks Very Much!
Please evaluate this session!
More questions? Contact us!
Rob Carr
Oklahoma ABLE Tech
rgcarr@okstate.edu
Jonathan Whiting
WebAIM