## Slide 1: Lessons Learned: Planning and Implementation of a Web Accessibility Initiative at The University of Alabama
Dr. Rachel Thompson
Director of Emerging Technology and Accessibility
Center for Instructional Technology
The University of Alabama

## Slide 2: Learning Objectives:
Understand the needs of diverse web teams with regard to accessibility evaluation and reporting.
Recognize when various types of testing, examples, and best practices can be most useful.
Determine how differences in reporting responsibilities, structures, & requirements can affect a11y progress.

## Slide 3: About The University of Alabama
Tuscaloosa, Alabama
Public, flagship institution
37,000+ students
12 colleges and schools
80+ undergraduate and 150+ graduate programs

## Slide 4: History of Accessibility at UA
Mid 2010- Initial discussions in Technology and Learning Committee
  Survey of student with disabilities
  Web site audit
Mid 2013:
  Assistive technology proposal funded
  Breaking the “chicken and egg” cycle
  Addressing legal concerns
  Executive request for web accessibility survey
Late 2014:
  Web accessibility audit shared with leadership and campus web teams
  President and provost request realistic phased plan to move forward with making accessible UA’s web and instructional technology, including implementation details and justification for resources the broader UA community might need.
“The first step to making UA’s technology accessible is adopting web accessibility guidelines, which will give a clear-cut basis for future phases of this initiative and should address the most needs not currently met through accommodations.”

## Slide 5: UA’s Web Landscape
Little functional governance
Dedicated web teams
Web teams for hire
Outsourced web development, design, templates, management
Non-web staff or faculty handling institutional web development, design
Various CMS: WordPress, OU Campus, Drupal, Joomla
Variety of content manager roles and responsibilities

## Slide 6: Reaching Consensus
Early 2015: meetings with 30+ campus web teams or individual web staff members to gauge readiness and needs
“Guidelines” versus “Policies”
Who decides resources and timeline?
Where should web a11y live
“UA web groups agree the World Wide Web Consortium Web Content Accessibility Guidelines Level A and AA are attainable within a proposed timeline of four years, if appropriate tools and support can be provided.”

## Slide 7: Web Team Needs
With web team consensus, start with public and campus wide web, with caveats for legacy and archive: “We can do this as long as we have adequate resources, but request that campus leaders recognize this is an important initiative to UA administration”
4 year timeline to reach WCAG 2.0 AA (includes A)
Support for resources, tools, training, adapting work processes
Adopted and announced guidelines
Funding for web accessibility evaluation, reporting, and training tools and or services
Web teams will create, submit, and implement plans (with help if they want)
Technical resource to support campus needs and test vendor claims (4 years to start)
Student workers to assist with plan and document remediation
Captioning grants

## Slide 8: Needs Assessment: Content
Compiling everyone’s initial requests and surveying to determine priorities
Content types:
  Forms
  PDFs
  Mobile content
  Dynamic content
  Images
  Multimedia (including video and audio)
  Microsoft Office files
  Password-protected content
  CMS needs

## Slide 9: Needs Assessment: Capabilities
Survey respondents indicated that the following capabilities would be useful for accessibility evaluation (in decreasing order of importance):
  Run reports/audits on demand
  Offer information on how to remedy accessibility problems
  Locate and evaluate multimedia, PDFs, and documents
  Allow evaluation for password-protected sites
  Single or multiple page evaluation and reporting available
  Run unlimited reports/audits (i.e. no limit to the number of pages evaluated)
  Browser-based option available
  Ability to ignore and reset rules or define exceptions
  Evaluate pre-published content (on a test server, page preview, or other non-published resource)
  Show progress/changes over time
  Ability to tie into UA authentication for single sign-on

## Slide 10: Finding the right tools for our campus
Request for Proposals
Vendor submissions and demonstrations
Collecting feedback and making decisions

## Slide 11: Implementation
Single-Sign On
Baseline audits
Vendor training
UA-led training
Web plan creation

## Slide 12: Training Considerations
Developer vs. Content Creator
Addressing varied needs and expectations
Types of testing
AMP Adjustments

## Slide 13: Making Plans
  Address new, existing, archive/legacy, vendor content
  Phased approach with dates
  Progress reporting
  Contact information
  Plan for revisiting and revising the plan

## Slide 14: About AMP
UA-specific information
  Number of users
  Typical issues and questions
SSB Bart Group overview

## Slide 15: Questions? Comments?
  SSB Bart Group
  Jason Crossett, Jason jason.crossett@ssbbartgroup.com
  Dr. Rachel S. Thompson, rsthompson2@ua.edu