## Slide 1: Promoting Document Accessibility Efforts and PDF Remediation Options
Gaby de Jongh, IT Accessibility Specialist, UW-IT Assistive Technology Services
Ana Thompson, Learning & Access Designer, UW Bothell
Notes: The University of Washington Accessible Technology Services implemented a Pilot Project to explore the complexities, financial cost, and time commitments facing departments when implementing State Policy #188 on IT accessibility.
We would like to share with you our experience and outcomes of the Pilot. The Pilot program was initiated on the Bothell and Tacoma campuses of UW as a test case before being implemented at the Seattle campus.
Goal of the project: increase awareness of the need to create accessible documents, and outreach to identify accessibility evangelists within units.

## Slide 2: Problem Statements
A significant amount of documents are created by UW Faculty, Staff, and Students each quarter.
These documents are often inaccessible, providing barriers for individuals with disabilities.
Instructors often find, acquire, or create content without accessibility support at the time of acquisition or creation.
Disability Resources for Students does not have enough lead time to proactively create accessible documents for students with disabilities.
Faculty often do not have the time, expertise, or resources to make accessible documents.
  Thus, faculty may experience additional stress or frustration in providing accessible documents, despite their desires to do so.
Students with disabilities at UW systemically face barriers regarding accessible documents.
Notes: First, let’s look at the issues.

## Slide 3: Forward Facing Documents
PDF Accessibility Tool
Google scan: January 8, 2017
Review statistics
  added by date
  by subdomain
  by unit/department
  track trends over time
Notes: Show PAT

## Slide 4: LMS Numbers
Winter Quarter 2018
  Number of classes in Canvas – 3,817
  Total # of documents distributed through Canvas – 349,058
  Average documents per class in Canvas – 91
Notes: These numbers were provided by DRS and are indicative of the Seattle campus only, does not include Tacoma or Bothell satellites.

## Slide 5: Top 5 Issues with Documents at UW
The document is scanned but not OCRed
  average per quarter – 17,498
The document has contrast issues
  average per quarter – 57,345
The document is untagged
  average per quarter – 51,213
The document does not have any headers
  average per quarter – 38,134
The document has images without alternative descriptions
  average per quarter – 36,781

## Slide 6: Summary of the Pilot
Seed funding obtained from UW-IT
Identify and achieve buy-in from leaders at satellite campus
  Including support staff
Identify PDF remediation vendors
Offer to purchase Adobe Acrobat Pro DC to help with remediation efforts
Offer training on Document Accessibility and PDF remediation
Notes: Seed money = $25K
Buy-in from Vice Chancellors office

## Slide 7: Bothell - PDF Pilot
Immediate Work
  Focus on uwb.edu website electronic documents
  Generate large report with all PDF locations (Siteimprove)
  Organize PDFs by website directory & primary web contact
  Email reports to the primary contact to coordinate/delegate
    Deadline with regular email reminders containing suggestions and resources for help
Notes: We decided to focus solely on the PDFs and other electronic documents located on our main website because of the high risk factor of it being available to the public. Student’s already have access to help with remediating electronic documents through the DRS office.

## Slide 8: Bothell - Buy-in & Options
Informed participants
  Accessibility isn’t optional
  Pilot was a free but a limited time opportunity
Offered a method to sort information + consultation meetings
Participants needed to verify relevant PDFs
  Campus-wide problem of too much content and lack of maintenance
Available options
  Vendor: $9.23/page with Vastec (free for pilot)
  Campus trainers: Ana (Bothell) & Gaby (Seattle)
  Self-teaching & remediation resources
  uw.edu/accessibility
  training on Lynda.com

## Slide 9: Bothell - PDF Pilot by the numbers
Total from Report: 2,943 PDFs
  Run April 2017
Active PDFs: 2,277
  Removed links to external PDFs
  Removed broken or duplicate PDFs
PDFs submitted for remediation: 122
  Pilot engagement was voluntary
  Constraints:
  Time
  Lack of supervisor support
  17 uwb.edu directories were updated out of about 140+ directories

## Slide 10: Bothell - Pilot Takeaways
HTML (web pages) - most accessible format
  Ask the question…
  Move info from documents → web pages
  Range of accessibility by platform:
    HTML → MS Office docs → PDFs → PDF Forms
Research what colleagues do, utilize skills and share the load
  Developer from IT pulled PDF report, then it was sorted/organized
Avoid mass submissions with vendor
  Complicated/time consuming to organize and redistribute
  Better to submit by web directory
Change culture to avoid “knee-jerk” reaction of using PDFs
  Changing workflows are faster than training on and doing PDF remediation
  If unavoidable: train 2-3 team members and/or budget for vendor remediation

## Slide 11: Bothell - Long Term Action Plan (1 of 2)
UDAL Initiative
  UDAL = Universal Design for Active Learning
    Established March 2016
  Comprises principles, research and best practices of Universal Design for Learning (UDL), Universal Design for Instruction (UDI) and accessibility (added emphasis on student engagement and physical spaces)
  UDAL Core Team formed June 2016
    IT, DLI, Advancement, DRS representation
Notes: UDAL work began prior to PDF pilot but was able to utilize and promote UDAL group and IT Accessibility Liaison work through this pilot.
Andreas Brockhaus, DLI Director, coined the name of the UDL initiative at UW Bothell.
The UDAL Core Team members are: Jeane Marty (IT), Ana Thompson (DLI), Ashley Magdall (Advancement), and Rosa Liu (DRS).

## Slide 12: Bothell - Long term action plan (2 of 2)
Accessibility Plan
  Committee formed November 2017
  Plan proposal finalized September 2018
  First leadership approval done October 2018
Training & Remediation
  Training sessions with IT Liaisons, Commuter Services, Community Based Learning & Research (CBLR), Student Affairs, Academic Affairs, Administration and Planning, Librarians, Teaching & Learning Center
  Adobe Acrobat Pro licenses for IT Liaisons (purchased by UW IT)
  Limited remediation services

## Slide 13: The Tacoma Method
AutoBatch for Adobe Acrobat Pro
  Automated remediation process
  Triggers “Autotag Document” feature in Acrobat Pro
Overwrites old files
Status of each document is documented
Notes: UW-Tacoma identified approximately 80,000 PDF documents linked from their web domain by programming a custom script that recursively parsed through the directories to find the PDF documents. After initial review, it was deemed too difficult to determine which files were no longer in use and which files should be kept due to the large number of documents. They purchased AutoBatch plug-in Software Functionality (available for $250) for Adobe Acrobat Pro which allows for an automated remediation process. The plug-in takes the documents identified by the script, passes them through to Adobe Acrobat Pro and triggers the “Autotag Document” feature; it then passes them back and overwrites the old files with the remediated document. The status of each document is captured in a database and notes if the document was able to be remediated. If the document could not be automatically remediated, manual remediation would be completed by a document creator. To date, Tacoma has processed about 25,000 PDF files.
This method does not conform to WCAG 2.0, Level AA. But it does address a large backlog of completely inaccessible documents.

## Slide 14: Overall Conclusions (1of 2)
Develop a plan for addressing accessibility of new documents
  Train document creators how to create accessible documents moving forward.
  Implement a departmental policy that requires all documents to be checked for accessorily before posting.
  Submit complex inaccessible PDF documents to a vendor for remediation (legacy documents).
Notes: Ensure documents are WCAG 2.0, Level AA compliant

## Slide 15: Overall Conclusions (2 of 2)
Determine the number of electronic documents published on sites
  How many are accessible?
Determine which documents are orphaned
  Develop a plan to deprecate them
Determine if there are compelling arguments for posting documents in HTML opposed to PDF
  Develop a plan for converting documents to HTML if possible (forms)

## Slide 16: Successful Practices/Lessons Learned
Successes
  Identify your advocates
  Understand the workflow
  Partner with Disability Resources for Students (DRS)
Lessons
  Focus on low hanging fruit
  Be aware of your approach
  Have resources in place

## Slide 17: Resources
UW-IT Assistive Technology Services Website
UW Bothell Accessibility Website