# Change Management Checklist for Scaling Technology Impact

A step-by-step guide for campus teams to plan, launch, and sustain successful technology adoption and engagement.

## 1. Pre-Launch Planning

Goal: Build clarity, alignment, and readiness before rollout.

### Foundational Prep

- Confirm institutional goals the tool supports (e.g., accessibility, retention, UDL).

- Identify key stakeholder groups (faculty, students, IT, DS, advising, tutoring, leadership).

- Clarify roles & responsibilities for implementation (project owner, champions, support contacts).

- Define “success” and identify key metrics (usage, engagement, course penetration, outcomes).

- Develop a simple 90-day launch plan or timeline.

### Campus Alignment

- Conduct pre-launch alignment meetings with core departments.

- Secure leadership buy-in and/or messaging support.

- Ensure workflows are mapped (how faculty/students access the tool, training, support path).

## 2. Awareness & Communication Strategy

Goal: Ensure people know what the tool is, why it matters, and how to use it.

### Messaging

- Craft audience-specific value propositions (faculty, students, DS, support staff).

- Connect the tool to widely understood campus needs (accessibility, accommodations, student support, inclusive teaching).

- Create or obtain clear “how to get started” instructions for each audience.

### Communication Channels

- Email announcements (multi-part sequence).

- LMS announcements or banners.

- Department meeting visits or presentations.

- Implementation microsite or resource hub.

- Student-facing campaigns (orientation, First-Year Experience, tutoring centers, ambassadors).

## 3. Training & Capacity Building

Goal: Empower people to feel confident and supported.

### Faculty / Staff Development

- Offer multiple training options (live workshops, asynchronous videos, office hours).

- Integrate training into existing PD events (CTL workshops, accessibility week, orientation).

- Develop quick-reference guides and short instructional videos.

- Identify and train “super users”, student/peer ambassadors or champions within departments.

### Student Support

- Train DS office, tutoring center, advising, student ambassadors and front-line staff.

- Provide student-facing instructions embedded where they naturally are (LMS, library, orientation).

## 4. Launch Execution

Goal: Roll out the tool smoothly with clear guidance and strong visibility.

- Send launch communications and reminders on schedule.

- Update LMS / SIS / websites with instructions and quick links.

- Host kickoff sessions or awareness events.

- Provide hands-on opportunities (demo booths, webinars, “pop-up help” sessions).

- Ensure support channels (IT tickets, email alias, vendor support) are set up and clear.

## 5. Engagement Monitoring & Data Tracking

Goal: Understand what is working and what needs attention.

### Metrics

- Track key usage indicators (logins, feature adoption, course penetration, uploads/usage patterns).

- Compare activity across departments or student populations.

- Identify high-usage champions and low-engagement areas.

- Monitor accessibility/equity trends.

### Feedback Loops

- Collect qualitative feedback (faculty surveys, student focus groups, DS insights).

- Schedule quarterly data reviews with internal teams and the vendor.

- Use data to refine messaging, training, and outreach.

## 6. Sustainment & Long-Term Integration

Goal: Transition from “new tool” to routine campus workflow.

### Ongoing Actions

- Create repeating campaigns at key academic moments (start of term, midterms, finals).

- Embed reminders into annual processes (syllabus reviews, faculty onboarding, accessibility checklists).

- Refresh and re-share training materials yearly.

- Maintain champions network with ongoing updates and recognition.

- Celebrate success stories and share impact data with leadership and campus partners.

### Continuous Improvement

- Revisit implementation goals annually.

- Adjust strategy based on usage patterns and outcomes.

- Build the tool into policy and practice to ensure consistency over time.