# 90-Day Accessibility Starter Plan

## Why This Plan Works

This plan fits cities, colleges, nonprofits, and one-person accessibility teams. It’s simple, practical, and designed for building quick wins.

## Big Picture Roadmap

[Weeks 1–2] Map Reality
↓
[Weeks 3–6] Pick One System
↓
[Weeks 7–12] Lock It In and Grow

## Weeks 1–2: Map Your Reality

### Identify Top Content & Systems

| Category | What to List | Examples |
| --- | --- | --- |
| Top Pages | 20 most-visited | Pay bill, permits, class schedule |
| Top Documents | 10 frequently used | Forms, policies, agendas |
| Core Systems | 5 critical systems | LMS, HR, payment portals |

### Identify Who Creates Content

Survey teams to find document creators, website editors, and system owners.

### Test One Page, Document, and System

Use WAVE, NVDA, keyboard-only navigation, and Acrobat’s accessibility checker to find friction points.

### Talk to Leadership

Clarify priorities, timelines, and available support.

### Outcome After Week 2

You now understand what matters most and where to start.

## Weeks 3–6: Pick One System

Choose one system to build:
- Document Pipeline
- Training Kit
- Vendor Workflow
- Accessibility Statement

### System Examples

Document Pipeline:
- Provide templates
- Teach headings/alt text/links
- Require no new inaccessible PDFs
- Remediate top documents
- Track quality

Training Kit:
- 1-page guides
- 30-minute session
- Identify a champion

## Weeks 7–12: Lock It In and Grow

- Make processes repeatable
- Train one more person
- Add one more department
- Report progress

### Example 90-Day Progress Summary

High-priority documents: 12 remediated
Staff trained: 14 across two departments
Vendor reviews: 1 complete, 1 scheduled
Next 90 days: Expand to Planning

## Common Pitfalls

- Trying to fix everything at once
- Training the whole org too early
- Starting with resistant departments
- Waiting for budget or consultants
- Trusting VPATs without testing

## Stretch Goals

Optional enhancements:
- Build a dashboard
- Launch champions group
- Create remediation calendar

## Key Takeaway

Start small. Pick one system, one department, one metric.